## Sheet1
Problem | Loss | Prob | Risk | Plan
Laptop may be lost, or files may become corrupted. | 4 | 1 | 4 | Use git version control to manage the code version on a separate server (github).
Difficulty implementing adversarial swarm. | 3 | 2 | 6 | Ask supervisor for help, as he is very experienced in producing simulations. If this fails, consulting more literature to fully understand how adversarial swarms generally work.
It is impossible to change the behaviour of the boids model when it is settled with the use of individual swarm members only. | 4 | 3 | 12 | Introduce the adversarial approach early, implementing shepherding behaviours from well known literature to achieve a similar behaviour.
Running out of time to complete both the swarm control and swarm fragmentation | 5 | 3 | 15 | Set strict deadlines for the implementations to be completed by. If the deadline for the swarm control section is not hit, the swarm fragmentation can be started anyway, since these two approaches are mutually exclusive. This way, the worst case scenario will be a partially report on one or both of the approaches.